## Sheet1
S.No. | Task Details | Login Id | Start Date | Dead Line | Assigned Hrs | Today Hrs | Working Hrs | Remainig Hrs | Status | Comments
1 | Scheme with Interest : bonus journal entry not create, bonus round off trial balance issue | Requirement Pragati Jewellers | 2024-11-19 | 2024-11-19 | 4 | 0 | 3 | 1 | Done | 2024-11-19: Work on create bonus journal entries (3 hrs)
2 | Prepare and test CAD add stock and sell files | Gemmagems | 2024-11-19 | 2024-12-03 | 30 | 4 | 23 | 7 | Working | 2024-11-19: Add cad stock files done send to testing (3hrs) 2024-11-26: solving cad add stock and sell testing issues.(2hrs) 2024-11-29: solving cad add stock and sell testing issues.(1.30hrs)+ Sonigra on call provide update and take req. (30min) 2024-02-03: solving cad add stock and sell testing issues. 2024-02-09: solving cad add stock and sell testing issues.(1hrs) 2024-02-16: solving cad add stock, sell, purchase testing issues.(5hrs) 2024-02-20: solving cad add stock, sell, purchase testing issues.(4hrs) 2024-02-21: solving cad add stock, sell, purchase testing issues.(4hrs)
3 | raw metal stock move to stock issue | cb619 | 2024-11-19 | 2024-11-19 | 1 | 0 | 1 | 0 | Done | 2024-11-19: Checking why this issue occurs in new build, then new report found. (1hrs)
4 | Invoice not showing on sold out list | RahulSoni | 2024-11-19 |  | 1 | 0 | 1 | 0 | Not Solve
5 | Trial Balance match/ New jrnl Upd/ freez | RRJEWELLERS | 2024-11-19 | 29-Nov-2024 Extended 03-Dec-2024 Due to loan issues 05-Dec-2024 Due to Finance | 60 | 0 | 53 | 7 | Working | 2024-11-20: 1. settled amount entry not added.(2hrs) 2. checking trial balance not match.(1hrs) 2024-11-21: 1. Settled amount journal entry creating issue. (2hrs) 2024-11-22: 1. Checking old upd, worked on it (3hrs). 2. creating new upd, done add stock & stone, sell stock (5hrs). 2024-11-23: 1. Done Advance and udhaar entries (3hrs). 2. working on mulriple sell entries inerted. (2hrs) 2024-11-25: 1. Done Purchase fine, recreate journal entries (2hrs). 2. Done Item return sell entries (2hrs). 2024-11-26: 1. Done Purchase stone, add stone, sell stone recreate journal entries (2hrs). 1. Done Purchase rawMetal, add rawMetal, sell rawMetal recreate journal entries (1hrs). 2024-11-26: 1. checking avail retail stock with category and silver stock report mismatch and provide solution. (3hrs) 2024-11-27: 1. Done previous amount settled amount jrnl entries. tested with RR jewellers DB and solve some entries insert multiple times. (6hrs) 2024-11-28: 1. Working on fine purchase stone multiple entries issue.(2hrs) 2024-12-02: 1. Udhaar Deposite, raw metal receive and paid journal entries done. (2hrs) 2. Solve Entries repeat. (1hrs) 2. Solving RR jewelers database issue solve. (3hrs) 2024-12-03: 1. Scheme Emi paid jrnl upd create.(2hrs) 2. raw metal paid and recived issue solve. (2hrs) 2024-12-04: 1. Creating finance jrnl entries,(4hrs); 2024-12-05: 1. Creating finance emi paid jrnl entries,(6hrs); 2024-12-07: 1. Tested on Shivanadaj Database scheme entries.(1hrs) 2024-12-19: 1. Working on loan journal entries. Loan add, loan deposit, principal amount done, 2. Testing on new all entries database and solving issues for same. (4hrs)
6 | Scheme EMI skip option/ order panel issues | ARUN9166 | 2024-11-19 |  | 50 | 4 | 12 | 38 | Working | 2024-12-07: 1. Remove red color from scheme invoice. 2. Scheme emi invoice t&c showing scroll. 3. Added height to customer sign.(1hrs) 2024-12-11: 1. Start working skip option, added skip emi option, started backend insert new row code with new start and end date.(7 hrs) 2024-12-21: 1. after due skipped option all emi are rollback working(4hrs)
7 | Quotation New panel | SKYGOLD | 2024-11-19 |  | 24 | 0 |  | 24 | Pending
8 | Loan Requirements | SONIGRA | 2024-11-19 |  | 24 | 0 | 12 | 12 | Done | 2024-11-28: 1. Call done with customer, provide then req. demo (1hrs)
9 | Sell Item delete issue | Sundram | 2024-11-19 |  | 4 | 0 |  | 4 | Not Started
10 | Multiple pay scheme emi | Shrivasthava | 2024-11-19 |  | 8 | 0 |  | 8 | Working
11 | Jewellery Panel quotation issues | 24CARAT | 2024-11-20 | 2024-11-20 | 2 | 0 | 2 | 0 | Done | 2024-11-20: 1. Other charges added in fx then valuation wrong showing (1hrs) 2. Gst Amount not showing in quotation. 3. Image added in quotation (1 hrs)
12 | Stock Mismatch/ Stock Reset | YourChoice | 2024-11-20 | 2024-11-20 | 2 | 0 | 2 | 0 | Done | 2024-11-20: 1. Delete avialble retail stock.(1 hrs) 2. balance raw metal stock.(1hrs)
13 | Metal Balance wt sum not showing | carat.24 | 2024-11-20 | 2024-11-20 | 1 | 0 | 1 | 0 | Done | 2024-11-20: 1. metal wt sum not showing. 2. some accounts not showing in account panel (1hrs)
14 | Rate add isue, taking long time | alka1956 | 2024-11-20 | 2024-11-20 | 1 | 0 | 1 | 0 | Done | 2024-11-20: 1. due to led indicator on, rate add taking long time. (1hrs)
15 | If loan provide with payment mode, then it not showing loan details | TAHELKA | 2024-11-21 | 2024-11-21 | 4 | 0 | 4 | 0 | Done | 2024-11-21: 1. Req. Shown payment details on loan details. (4hrs)
16 | Item profit loss issue | Jeelan Jewellers | 2024-11-21 | 2024-11-21 | 1 | 0 | 1 | 0 | Done | 2024-11-21: 1. Customer added stock with 0 rate, p/l showing wrong (1hrs)
17 | Previous stone not showing in payment panel | TESTER | 2024-11-21 | 2024-11-21 | 1 | 0 | 1 | 0 | Done | 2024-11-21: 1. for settle previous stone not showing on payment panel. (1hrs)
18 | Order Invoice delete not showing | ARUN9166 | 2024-11-21 | 2024-12-05 |  | 0 | 0 | 0 | Not Started
19 | Change item purity which > 700 | MADAN321 | 2024-11-21 | 2024-12-20 |  | 0 | 0 | 0 | Not Started
20 | Loan Interest issue | Daksh1 | 2024-12-10 | 2024-12-10 | 8 | 0 | 5 | 3 | Done | 2024-12-10: 1. Solve compound interest issue for 2 year and 3 years, and provided to customer. (5hrs)
21 | Jewellery Panel diamond valuation issue | CARAT24 | 2024-11-23 | 2024-11-23 | 2 | 0 | 2 | 0 | Done | 2024-11-23: 1. checking diamond valuation not showing on jewellery panel, discussion and solution. (2hrs)
22 | Add stock items other iinfo not showing in sell panel |  | 2024-11-23 | 2024-11-23 | 1 | 0 | 1 | 0 | Done | 2024-11-23: 1. when add stock with other info, at a time of sell its not showing
23 | Final fine weight setting in jewellery panel | NAYANA | 2024-11-25 | 2024-11-25 | 4 | 0 | 4 | 0 | Done | 2024-11-25: 1. added final fine weight by settings in jewellery panel (4hrs)
24 | Stock Mismatch check and solution | CHETAN S | 2024-11-26 | 2024-11-26 | 10 | 0 | 6 | 4 | Working | 2024-11-26: 1. checking avail retail stock with category and silver stock report mismatch and provide solution. (3hrs) 2024-12-07: 1. Checking Category wise stock mismatch issue. (3hrs)
25 | In ledger Gst Report by sell inv showing wrong payment mode values when amount return to customer | MohitJewellers | 2024-11-27 | 2024-11-27 | 1 | 0 | 1 | 0 | Done | 2024-11-27: 1. showing minus amount in GST REPORTS -> GST SELL REPORT BY INV (1hrs)
26 | KT and Birthday |  |  |  | 2 |  | 2 | 0 | Done
27 | Loan Interest issue | SumitRaj and Soni173 | 2024-11-28 | 2024-12-02 | 18 | 0 | 11 | 7 | Working | 2024-11-28: 1. interest showing wrong on 30 and 31 day case. issue solved files provide to customer he will check and confirm(5hrs). 2024-11-29: 1. .
28 | FILES REVIEW and Preparation |  |  |  | 2 | 0 | 2 | 0 | Done | 2024-12-02: 1. Review dnynaeshwari stock transfter 15 files. Review sans files. 2. prepare joint loan files. 3. prepare tahelka loan req. files. 4. prepare CAD files.
29 | Customer on call |  |  |  | 3 | 0 | 3 | 0 | Done | 1. Sonigra - update on loan req. and solve daubt 2. scheme req. with GAURAV JAWANJAL 2024-12-04: 1. Sonigra on call.(0.5 hrs) 2. Ashish02 image download issue.(1.5hrs) 3. Ranka.Jeweller@ and VaradJewellers : solve final fine wt calculation issue.(1hrs) 2024-12-09: 1. Carat24 : scheme req. 2. Gurukrupa Gems : Req. Discuss 3. Sonigra : Update on req. 2024-12-11: 1. Sonigra on call, 2 times.(0.5 hrs) 2024-12-12: 1. Sonigra on call 2. Atul Malunjkar call and stock mismatch discussion 3. NidhiFinanace. 4. Sending mails to customer.(2hrs) 2024-12-13: 1. NidhiFinanace demo.(1hrs)
30 | stock mismatch--fix each n every panel | maniratnam |  |  | 35 | 0 | 8 | 27 | Working | 2024-12-13: 1. Analyasing stock mismatch and updating with o gs weight. (2hrs) 2024-12-16: 1. Working on stock mismatch issue, found 3 major issue scause stock mismatch, solve 2(3 hrs) 2024-12-19: 1. working on minus partisal sell + AFM and RFM stock from stock table. upd done. (4hrs). 2024-12-20: 1. working on minus partisal sell + AFM and RFM stock from stock table. upd done. (2hrs).
31 | User transaction entry deleted | NEW KAKASHRI | 2024-12-05 | 2024-12-06 | 2 | 0 | 2 | 0 | Done | 2024-12-05: 1. Customers sell invoice deleted, recreated.(1hrs) 2024-12-09: 1. Customers sell invoice deleted, recreated.(2hrs)
32 | RateCut and NoRateCut explanation |  | 2024-12-05 | 2025-01-11 | 1 | 0 | 1 | 0 | Done | 2024-12-05: 1. RateCut and NoRateCut explanation to Chetan for mobile app.(1hrs)
33 | Daybook scheme multiple entries issue | SHIVANANDAJ | 2024-12-06 | 2024-12-07 | 2 | 0 | 2 | 0 | Done | 2024-12-07: 1. Deleted multiple created entries also jrnl entries. (2hrs)
34 | Customer want sell invoice old layout for item name and final amount | CKSARAF | 2024-12-07 | 2024-12-07 | 2 | 0 | 2 | 0 | Done | 2024-12-07: 1. As per customer need removed hard coded width, and added auto width.(2hrs)
35 | Multiple staff login invoice no issue |  | 2024-12-09 | 2024-12-23 | 32 | 0 | 6 | 26 | Working | 2024-12-09: 1. added code to bypass invoice already present. (4hrs). 2024-12-10: 2. added otimized code. and testing (2hrs) | ar
36 | Loan item image download issue | Tehlka | 2024-12-10 | 2024-12-10 | 3 | 0 | 1 | 2 | Done | 2024-12-10: 1. webcam image download issue. customer checking all images. (1hrs)
37 | Form 8 Req. | Nidhifinance3537 | 2024-12-12 | 2024-12-13 | 15 | 0 | 6 | 9 | Done | 2024-12-12: 1. Complete interest slab, hide whatspp logo and barcode done, getting knowledge of actual req. call with customer. (6hrs) 2024-12-13: 1. Loan last date, firm logo alignment issue, added code for all samples.Shown Loan item metal wise total details. (5hrs)
| Total Hrs |  |  |  | 361 | 8 | 182 | 179
i